## Sheet1
	Jan 25, 2024				Jan 29, 2024					Feb 05, 2024					Feb 12, 2024					Feb 19, 2024					Feb 26, 2024					Mar 04, 2024					Mar 11, 2024					Mar 18, 2024					Mar 25, 2024					Apr 01, 2024					Apr 08, 2024					Apr 15, 2024					Apr 22, 2024					Apr 29, 2024					May 06, 2024					May 13, 2024					May 20, 2024					May 27, 2024					Jun 03, 2024					Jun 10, 2024					Jun 17, 2024					Jun 24, 2024
	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S
	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
Report					Report due 14:00
				organize and attend project review meeting					bold			main milestones
				project health check up					subtasks
				supervisor meetings
				exam dead-zone

Source					Source due 14:00
				clean data
				implement baseline scripts
				construct baseline metrics
				actively research other source models for transfer

Presentation					Presentation
				Plan presentation
				Check Plan
				Write Slides
				Rehearse Slides
				Presentation day 19:00