## Sheet1
	Jan 25, 2024				Jan 29, 2024					Feb 05, 2024					Feb 12, 2024					Feb 19, 2024					Feb 26, 2024					Mar 04, 2024					Mar 11, 2024					Mar 18, 2024					Mar 25, 2024					Apr 01, 2024					Apr 08, 2024					Apr 15, 2024					Apr 22, 2024					Apr 29, 2024					May 06, 2024					May 13, 2024					May 20, 2024					May 27, 2024					Jun 03, 2024					Jun 10, 2024					Jun 17, 2024					Jun 24, 2024
	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S
	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
Report					Report due 14:00
				organise a visit to Marsden Hospital					bold			main milestones
				organize and attend project review meeting					subtasks
				document potential for data augmentation					review report so far					supervisor meetings
				document and discuss baseline metrics					document alternative approaches					update pre-written interim sections where required					exam dead-zone
				project health check up					formalise results
				discussion and future work
				supervisor peer-review
				student peer-review
Source					Source due 14:00
				clean data
				implement baseline scripts
				construct baseline metrics
				write foundation of transfer learning for hyper-parameter tuning
				tune network
				consider optimisations for current network
				consider alternative approaches to solving problem
				review code so far
				complete loose ends
				consider data augmentation to produce a more accurate prediction
				consider improvements on current architecture
				consider alternative approaches
				Fine-tune approach

				tidy up remainder of code

Presentation					Presentation
				Plan presentation
				Check Plan
				Write Slides
				Rehearse Slides
				Presentation day 19:00